## Instructions
How to use the Test Log
Enter one test per row on the 'Test Log' sheet. The Summary and Weekly Summary sheets calculate automatically from those entries.
Use the drop-down lists for Week, Product, Translation Result, IWXXM Validation, Accuracy and Severity to ensure the formulas count results consistently.
For a failed or questionable result, also complete an Error Report and reference the file/screenshot in the Test Log.

## Test Log
Test ID | Week | Date | Product | TAC Message / Reference | Translation Result | IWXXM Validation | TAC vs IWXXM Accurate? | Severity | Issue / Comment | Screenshot / File Reference | Retest Result
T001(EXAMPLE-See Instructions Sheet) | Week 1 | 2026-09-08 | METAR | TTPP | PASS | PASS | YES | None
T002 | Week 1 | 2026-09-28 | TAF | TTPP | FAIL | FAIL | NO | Critical | 7000 VIS IS NOT FOR THE BECMG TREND | WEEK 1- TAF TESTING DATASET, IMAGE 1 | NOT RETESTED
T003 | Week 1 | 2026-09-28 | TAF | TTCP | FAIL | FAIL | NO | Critical |  | WEEK 1- TAF TESTING DATASET, IMAGE 2 | NOT RETESTED
T004 | Week 1 | 2026-09-28 | TAF | TUPJ | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 3 | NOT RETESTED
T005 | Week 1 | 2026-09-28 | TAF | TKPK | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 4 | NOT RETESTED
T006 | Week 1 | 2026-09-28 | TAF | TKPN | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 5 | NOT RETESTED
T007 | Week 1 | 2026-09-28 | TAF | TLPL | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 6 | NOT RETESTED
T008 | Week 1 | 2026-09-28 | TAF | TLPC | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 7 | NOT RETESTED
T009 | Week 1 | 2026-09-28 | TAF | TRPG | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 8 | NOT RETESTED
T010 | Week 1 | 2026-09-28 | TAF | TAPA | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 9 | NOT RETESTED
T011 | Week 1 | 2026-09-28 | TAF | TDPD | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 10 | NOT RETESTED
T012 | Week 1 | 2026-09-28 | TAF | TGPY | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 11 | NOT RETESTED
T013 | Week 1 | 2026-09-28 | TAF | TVSA | FAIL | PASS | NO | Major | MISSING WEATHER GROUP | WEEK 1- TAF TESTING DATASET, IMAGE 12 | NOT RETESTED
T014 | Week 1 | 2026-09-28 | TAF | TBPB | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 13 | NOT RETESTED
T015 | Week 1 | 2026-09-28 | TAF | MZBZ | PASS | PASS | YES | Minor | Missing Conversion/validation log | WEEK 1- TAF TESTING DATASET, IMAGE 14 | NOT RETESTED
T016 | Week 1 | 2026-09-28 | TAF | MKJP | PASS | PASS | YES | Major | EXCLUDED 'AMD NOT SKED' | WEEK 1- TAF TESTING DATASET, IMAGE 15 | NOT RETESTED
T017 | Week 1 | 2026-09-28 | TAF | MKJS | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 16 | NOT RETESTED
T018 | Week 1 | 2026-09-28 | TAF | TQPF | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 17 | NOT RETESTED
T019 | Week 1 | 2026-09-28 | TAF | MWCR | PASS | PASS | NO | Major | EXCLUDED A WEATHER GROUP TS | WEEK 1- TAF TESTING DATASET, IMAGE 18 | NOT RETESTED
T020 | Week 1 | 2026-09-28 | TAF | TNCM | PASS | PASS | YES | None |  | WEEK 1- TAF TESTING DATASET, IMAGE 19 | NOT RETESTED
T021 | Week 1 | 2026-09-28 | TAF | MBPV | PASS | PASS | NO | Major | EXCLUDED A WEATHER GROUP VCSH | WEEK 1- TAF TESTING DATASET, IMAGE 20 | NOT RETESTED
T022 | Week 1 | 2026-09-28 | TAF | MBGT | PASS | PASS | NO | Major | EXCLUDED A WEATHER GROUP VCSH | WEEK 1- TAF TESTING DATASET, IMAGE 21 | NOT RETESTED
T023 | Week 1 | 2026-09-29 | SPECI | TTPP | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 1
T024 | Week 1 | 2026-09-29 | SPECI | TUPJ | FAIL | PASS | NO | Major | EXCLUDED RMKS/ PRESENT WEATHER INVALID | WEEK 1-SPECI TESTING DATASET, IMAGE 2
T025 | Week 1 | 2026-09-29 | SPECI | TAPA | FAIL | PASS | NO | Major | PRESENT WEATHER INVALID | WEEK 1-SPECI TESTING DATASET, IMAGE 3
T026 | Week 1 | 2026-09-29 | SPECI | TBPB | FAIL | PASS | NO | Critical | EXCLUDED RECENT WEATHER AND VCSH IN PRESENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 4
T027 | Week 1 | 2026-09-29 | SPECI | TBPB | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 5
T028 | Week 1 | 2026-09-29 | SPECI | TBPB | FAIL | PASS | NO | Major | EXCLUDED A WEATHER GROUP VCSH | WEEK 1-SPECI TESTING DATASET, IMAGE 6
T029 | Week 1 | 2026-09-29 | SPECI | MWCR | FAIL | PASS | NO | Major | EXCLUDED A WEATHER GROUP VCSH AND TS | WEEK 1-SPECI TESTING DATASET, IMAGE 7
T030 | Week 1 | 2026-09-29 | SPECI | MWCR | FAIL | PASS | NO | Major | EXCLUDED A WEATHER GROUP VCSH | WEEK 1-SPECI TESTING DATASET, IMAGE 8
T031 | Week 1 | 2026-09-29 | SPECI | TAPA | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 9
T032 | Week 1 | 2026-09-29 | SPECI | MKJP | PASS | PASS | NO | Major | EXCLUDED RECENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 10
T033 | Week 1 | 2026-09-29 | SPECI | TJSJ | PASS | PASS | NO | Minor | INCORRECT CONVERSION OF THE SM IN METERS | WEEK 1-SPECI TESTING DATASET, IMAGE 11
T034 | Week 1 | 2026-09-29 | METAR | TBPB | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 12
T035 | Week 1 | 2026-09-29 | SPECI | MKJP | FAIL | FAIL | NO | Critical | MSSING TAC PRODUCT | WEEK 1-SPECI TESTING DATASET, IMAGE 13/14 | PASS
T036 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 15
T037 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 16
T038 | Week 1 | 2026-09-29 | SPECI | TNCM | FAIL | PASS | NO | Major | EXCLUDED RECENT WEATHER AND VCSH IN PRESENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 17
T039 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | NO | Minor | EXCLUDED RMKS AND RECENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 18
T040 | Week 1 | 2026-09-29 | SPECI | TNCM | FAIL | PASS | NO | Major | EXCLUDED CB CLOUDS AND RMKS | WEEK 1-SPECI TESTING DATASET, IMAGE 19
T041 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 20
T042 | Week 1 | 2026-09-29 | SPECI | TNCM | FAIL | PASS | NO | Major | DOES NOT RECOGNIZE VISIBILITY | WEEK 1-SPECI TESTING DATASET, IMAGE 21
T043 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | NO | Minor | EXCLUDED RECENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 22
T044 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | Minor | EXCLUDED RMKS | WEEK 1-SPECI TESTING DATASET, IMAGE 23
T045 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | Minor | Missing Conversion/validation log | WEEK 1-SPECI TESTING DATASET, IMAGE 24
T046 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | Minor | TRANSLATED WITHOUT THE TERMINATOR | WEEK 1-SPECI TESTING DATASET, IMAGE 25/26 | PASS
T047 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 27
T048 | Week 1 | 2026-09-29 | SPECI | TNCM | FAIL | PASS | NO | Major | INVALID TOKENS, EXCLUDED RMKS | WEEK 1-SPECI TESTING DATASET, IMAGE 28
T049 | Week 1 | 2026-09-29 | SPECI | TNCM | FAIL | PASS | NO | Major | DOES NOT RECOGNIZE VISIBILITY | WEEK 1-SPECI TESTING DATASET, IMAGE 29/30 | FAIL
T050 | Week 1 | 2026-09-29 | SPECI | TNCM | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 31
T051 | Week 1 | 2026-09-29 | SPECI | TBPB | FAIL | PASS | NO | Major | EXCLUDED A PRESENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 32
T052 | Week 1 | 2026-09-29 | SPECI | TBPB | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 33
T053 | Week 1 | 2026-09-29 | SPECI | TBPB | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHERS VCSH VCTS | WEEK 1-SPECI TESTING DATASET, IMAGE 34
T054 | Week 1 | 2026-09-29 | SPECI | TBPB | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER VCSH | WEEK 1-SPECI TESTING DATASET, IMAGE 35
T055 | Week 1 | 2026-09-29 | SPECI | TBPB | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER VCSH | WEEK 1-SPECI TESTING DATASET, IMAGE 36
T056 | Week 1 | 2026-09-29 | SPECI | TGPY | PASS | PASS | YES | Minor | EXCLUDED RMKS | WEEK 1-SPECI TESTING DATASET, IMAGE 37
T057 | Week 1 | 2026-09-29 | SPECI | TRPG | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 38
T058 | Week 1 | 2026-09-29 | SPECI | MWCR | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 39
T059 | Week 1 | 2026-09-29 | SPECI | MKJS | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 40
T060 | Week 1 | 2026-09-29 | SPECI | MKJS | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER TS | WEEK 1-SPECI TESTING DATASET, IMAGE 41
T061 | Week 1 | 2026-09-29 | SPECI | MZBZ | PASS | PASS | YES | None |  | WEEK 1-SPECI TESTING DATASET, IMAGE 42
T062 | Week 1 | 2026-09-29 | SPECI | MZBZ | PASS | PASS | NO | Minor | RESH IS INVALID - CHANGED TO RESHUP | WEEK 1-SPECI TESTING DATASET, IMAGE 43
T063 | Week 1 | 2026-09-29 | SPECI | MZBZ | PASS | PASS | NO | Minor | EXCLUDED RMKS | WEEK 1-SPECI TESTING DATASET, IMAGE 44
T064 | Week 1 | 2026-09-29 | SPECI | MZBZ | PASS | PASS | NO | Minor | EXCLUDED RMKS AND RECENT WEATHER | WEEK 1-SPECI TESTING DATASET, IMAGE 45
T065 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 1
T066 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 2
T067 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 3
T068 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 4
T069 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 5
T070 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 6
T071 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 7
T072 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 8
T073 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 9
T074 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | Minor | EXCLUDED RMKS AND RECENT WEATHER | WEEK 1 METAR DATASET TTPP, IMAGE 10
T075 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 11
T076 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 12
T077 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 13
T078 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 14
T079 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 15
T080 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 16
T081 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 17
T082 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | Major | EXCLUDED RMKS AND RECENT WEATHER | WEEK 1 METAR DATASET TTPP, IMAGE 18
T083 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 19
T084 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 20
T085 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 21
T086 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 22
T087 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 23
T088 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 24
T089 | Week 1 | 2026-09-22 | METAR | TTPP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTPP, IMAGE 25
T090 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 1
T091 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 2
T092 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 3
T093 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 4
T094 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 5
T095 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 6
T096 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 7
T097 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 8
T098 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 9
T099 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 10
T100 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 11
T101 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 12
T102 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 13/14
T103 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 15
T104 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 16
T105 | Week 1 | 2026-09-29 | METAR | TTCP | PASS | PASS | YES | None |  | WEEK 1 METAR DATASET TTCP, IMAGE 17
T106 | Week 1 | 2026-09-29 | METAR | TTCP | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER AND REMARKS | WEEK 1 METAR DATASET TTCP, IMAGE 18
T107 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 1
T108 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 2
T109 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 3
T110 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 4
T111 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 5
T112 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 6
T113 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 7
T114 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 8
T115 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 9
T116 | Week 1 | 2026-09-29 | METAR | TUPJ | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER AND VISIBILITY | WEEK 1 METAR DATASET TUPJ, IMAGE 10
T117 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 11
T118 | Week 1 | 2026-09-29 | METAR | TUPJ | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER AND VISIBILITY | WEEK 1 METAR DATASET TUPJ, IMAGE 12
T119 | Week 1 | 2026-09-29 | METAR | TUPJ | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER AND VISIBILITY | WEEK 1 METAR DATASET TUPJ, IMAGE 13
T120 | Week 1 | 2026-09-29 | METAR | TUPJ | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER AND VISIBILITY | WEEK 1 METAR DATASET TUPJ, IMAGE 14
T121 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | YES | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 15
T122 | Week 1 | 2026-09-29 | METAR | TUPJ | FAIL | PASS | NO | Major | EXCLUDED PRESENT WEATHER AND VISIBILITY AND RMK | WEEK 1 METAR DATASET TUPJ, IMAGE 16
T123 | Week 1 | 2026-09-29 | METAR | TUPJ | PASS | PASS | NO | Minor | EXCLUDED REMARKS AND VISIBILTY | WEEK 1 METAR DATASET TUPJ, IMAGE 17
T124 | Week 2 | 2026-09-14 | TAF | MZBZ | PASS | PASS | YES | Minor | SOFT PREVIEW WAS UNCHECKED | TAF MZBZ WEEK 2, IMAGE 1
T125 | Week 2 | 2026-09-14 | TAF | MZBZ | PASS | PASS | YES | Minor | SOFT PREVIEW WAS UNCHECKED | TAF MZBZ WEEK 2, IMAGE 2
T126 | Week 2 | 2026-09-15 | TAF | MZBZ | PASS | PASS | YES | Minor | SOFT PREVIEW WAS UNCHECKED | TAF MZBZ WEEK 2, IMAGE 3
T127 | Week 2 | 2026-09-20 | TAF | MZBZ | FAIL | PASS | YES | Minor | INVALID TIME FORMAT | TAF MZBZ WEEK 2, IMAGE 4/5 | PASS
T128 | Week 2 | 2026-09-20 | TAF | MZBZ | FAIL | PASS | NO | Major | PRESENT WEATHER INVALID | TAF MZBZ WEEK 2, IMAGE 6, MANUAL INPUT 3_2/6
T129 | Week 2 | 2026-09-20 | TAF | MZBZ | PASS | PASS | YES | Minor | SOFT PREVIEW WAS CHECKED FOR THE RETEST | TAF MZBZ WEEK 2, IMAGE 7/8 | PASS
T130 | Week 2 | 2026-09-20 | TAF | MZBZ | PASS | PASS | YES | None |  | TAF MZBZ WEEK 2, IMAGE 9
T131 | Week 2 | 2026-09-20 | TAF | MZBZ | FAIL | PASS | YES | Major | INVALID TIME FORMAT/ INCORRECT WINDS | TAF MZBZ WEEK 2, IMAGE 10/11 | PASS
T132 | Week 2 | 2026-09-21 | TAF | MZBZ | FAIL | PASS | YES | Minor | IDENTIFY VARIABLE WINDS BUT SPEED M/S | TAF MZBZ WEEK 2, IMAGE 12 | PASS
T133 | Week 2 | 2026-09-22 | TAF | MZBZ | PASS | PASS | YES | Minor | IDENTIFY VARIABLE WINDS BUT SPEED M/S | TAF MZBZ WEEK 2, IMAGE 13
T134 | Week 2 | 2026-09-23 | TAF | MZBZ | PASS | PASS | YES | None |  | TAF MZBZ WEEK 2, IMAGE 14
T135 | Week 2 | 2026-09-24 | TAF | MZBZ | PASS | PASS | YES | Minor | IDENTIFY VARIABLE WINDS BUT SPEED M/S | TAF MZBZ WEEK 2, IMAGE 15
T136 | Week 2 | 2026-09-25 | TAF | MZBZ | PASS | PASS | YES | Minor | IDENTIFY VARIABLE WINDS BUT SPEED M/S | TAF MZBZ WEEK 2, IMAGE 16
T137 | Week 2 | 2026-09-25 | TAF | MZBZ | PASS | PASS | YES | Minor | IDENTIFY VARIABLE WINDS BUT SPEED M/S | TAF MZBZ WEEK 2, IMAGE 17
T138 | Week 2 | 2026-09-25 | TAF | MZBZ | PASS | PASS | YES | Minor | IDENTIFY VARIABLE WINDS BUT SPEED M/S | TAF MZBZ WEEK 2, IMAGE 18
T139 | Week 2 | 2026-09-26 | TAF | MZBZ | PASS | PASS | YES | None |  | TAF MZBZ WEEK 2, IMAGE 19
T140 | Week 2 | 2026-09-26 | TAF | MZBZ | PASS | PASS | YES | None |  | TAF MZBZ WEEK 2, IMAGE 20
T141 | Week 2 | 2026-09-23 | METAR | MZBZ | PASS | PASS | NO | Major | INVALID PRESENT WEATHER TOKEN | METAR WEEK 2, IMAGE 1
T142 | Week 2 | 2026-09-23 | SPECI | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMKS AND RECENT WEATHER | METAR WEEK 2, IMAGE 2
T143 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMK | METAR WEEK 2, IMAGE 3
T144 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 4
T145 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 5
T146 | Week 2 | 2026-09-30 | METAR | MZBZ | FAIL | PASS | YES | None | INCOMPLETE WIND TOKEN | METAR WEEK 2, IMAGE 6/7 | PASS
T147 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | NO | Major | EXCLUDED RMKS AND PRESENT WEATHER | METAR WEEK 2, IMAGE 8
T148 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMKS AND RECENT WEATHER | METAR WEEK 2, IMAGE 9
T149 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 10
T150 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 11
T151 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 12
T152 | Week 2 | 2026-09-30 | METAR | MZBZ | FAIL | PASS | NO | Major | EXCLUDED RMKS AND PRESENT WEATHER | METAR WEEK 2, IMAGE 13
T153 | Week 2 | 2026-09-30 | METAR | MZBZ | FAIL | PASS | NO | Major | EXCLUDED RMKS AND PRESENT WEATHER | METAR WEEK 2, IMAGE 14
T154 | Week 2 | 2026-09-30 | SPECI | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMK AND RECENT WEATHER | METAR WEEK 2, IMAGE 15
T155 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 16
T156 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 17
T157 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 18
T158 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 19
T159 | Week 2 | 2026-09-30 | METAR | MZBZ | FAIL | PASS | NO | Major | EXCLUDED RMKS AND PRESENT WEATHER | METAR WEEK 2, IMAGE 20
T160 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMKS | METAR WEEK 2, IMAGE 21
T161 | Week 2 | 2026-09-30 | SPECI | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMKS | METAR WEEK 2, IMAGE 22
T162 | Week 2 | 2026-09-30 | SPECI | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMK AND RECENT WEATHER | METAR WEEK 2, IMAGE 23
T163 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 24
T164 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 25
T165 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 26
T166 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | NO | Minor | EXCLUDED PRESENT WEATHER AND RMKS | METAR WEEK 2, IMAGE 27
T167 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 28
T168 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 29
T169 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 30
T170 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 31
T171 | Week 2 | 2026-09-30 | METAR | MZBZ | FAIL | PASS | YES | Minor | INCOMPLETE CLOUD TOKEN | METAR WEEK 2, IMAGE 32/33 | PASS
T172 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMKS | METAR WEEK 2, IMAGE 34
T173 | Week 2 | 2026-09-30 | METAR | MZBZ | PASS | PASS | YES | None |  | METAR WEEK 2, IMAGE 35
T174 | Week 2 | 2026-09-30 | METAR | MZBZ | FAIL | PASS | YES | Minor | MISSING VISIBILITY TOKEN | METAR WEEK 2, IMAGE 36/37 | PASS
T175 | Week 2 | 2026-09-30 | SPECI | MZBZ | PASS | PASS | YES | Minor | EXCLUDED RMKS | METAR WEEK 2, IMAGE 38
T176
T177
T178
T179
T180
T181
T182
T183
T184
T185
T186
T187
T188
T189
T190
T191
T192
T193
T194
T195
T196
T197
T198
T199
T200
T201
T202
T203
T204
T205
T206
T207
T208
T209
T210
T211
T212
T213
T214
T215
T216
T217
T218
T219
T220
T221
T222
T223
T224
T225
T226
T227
T228
T229
T230
T231
T232
T233
T234
T235
T236
T237
T238
T239
T240
T241
T242
T243
T244
T245
T246
T247
T248
T249
T250
T251
T252
T253
T254
T255
T256
T257
T258
T259
T260
T261
T262
T263
T264
T265
T266
T267
T268
T269
T270
T271
T272
T273
T274
T275
T276
T277
T278
T279
T280
T281
T282
T283
T284
T285
T286
T287
T288
T289
T290
T291
T292
T293
T294
T295
T296
T297
T298
T299
T300

## Summary
Product | Messages Tested | Translation PASS | Validation PASS | Accuracy YES | Critical | Major | Minor
METAR | 91 | 79 | 91 | 78 | 0 | 12 | 20
SPECI | 46 | 29 | 45 | 22 | 2 | 16 | 15
TAF | 38 | 31 | 36 | 31 | 2 | 7 | 12
SIGMET | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 175 | 139 | 172 | 131 | 4 | 35 | 47

## Weekly Summary
Week | Purpose | Messages Tested | Translation PASS | Validation PASS | Accuracy YES | Critical | Major | Minor
Week 1 | Familiarisation and basic functionality | 123 | 97 | 120 | 86 | 4 | 28 | 24
Week 2 | Operational parallel testing | 52 | 42 | 52 | 45 | 0 | 7 | 23
Week 3 | Error testing and final evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0